## Execution Plan
Date | Task | Description | Status | % Completed | Notes
2026-03-11 | Day 1 — Project Skeleton | Create project repository | Done | 100% | Running project exists
2026-03-11 | Day 1 — Project Skeleton | Setup backend server structure | Done | 100% | FastAPI active
2026-03-11 | Day 1 — Project Skeleton | Configure environment variables | Done | 90% | Minor env hardening possible
2026-03-11 | Day 1 — Project Skeleton | Create base API endpoint for chat | Done | 100% | /chat working
2026-03-11 | Day 1 — Project Skeleton | Test POST /chat endpoint | Done | 100% | Verified earlier
2026-03-12 | Day 2 — Chat Interface | Create simple chat UI page | Done | 80% | Exists but not focus now
2026-03-12 | Day 2 — Chat Interface | Build message input box | Done | 90%
2026-03-12 | Day 2 — Chat Interface | Render message history | Partial | 70%
2026-03-12 | Day 2 — Chat Interface | Connect UI to backend endpoint | Done | 100%
2026-03-12 | Day 2 — Chat Interface | Test sending and receiving messages | Done | 100%
2026-03-13 | Day 3 — AI Connection | Integrate LLM API | Done | 100% | OpenAI wired
2026-03-13 | Day 3 — AI Connection | Create system prompt template | Done | 85% | Needs tightening
2026-03-13 | Day 3 — AI Connection | Send user message to model | Done | 100%
2026-03-13 | Day 3 — AI Connection | Return response to UI | Done | 100%
2026-03-13 | Day 3 — AI Connection | Verify conversation loop | Done | 90%
2026-03-14 | Day 4 — Clinic Configuration Engine | Create clinic_config.json structure | Done | 100%
2026-03-14 | Day 4 — Clinic Configuration Engine | Define service structure | Done | 100%
2026-03-14 | Day 4 — Clinic Configuration Engine | Load config into prompt | Done | 100%
2026-03-14 | Day 4 — Clinic Configuration Engine | Test service restriction logic | Partial | 75% | Edge cases missing
2026-03-14 | Day 4 — Clinic Configuration Engine | Validate configuration loading | Done | 90%
2026-03-15 | Day 5 — Symptom Interpretation Logic | Define symptom keywords | Done | 85%
2026-03-15 | Day 5 — Symptom Interpretation Logic | Map symptoms to services | Done | 80% | Matching is heuristic
2026-03-15 | Day 5 — Symptom Interpretation Logic | Improve AI prompt instructions | Partial | 70% | Weak control layer
2026-03-15 | Day 5 — Symptom Interpretation Logic | Test 10 symptom scenarios | Partial | 60%
2026-03-15 | Day 5 — Symptom Interpretation Logic | Refine response formatting | Done | 85%
2026-03-16 | Day 6 — Booking Integration | Create Calendly account | Pending | 0%
2026-03-16 | Day 6 — Booking Integration | Configure clinic calendar | Pending | 0%
2026-03-16 | Day 6 — Booking Integration | Generate booking link | Pending | 0%
2026-03-16 | Day 6 — Booking Integration | Integrate booking suggestion logic | Done | 85% | Logic exists internally
2026-03-16 | Day 6 — Booking Integration | Test booking flow | Partial | 65%
2026-03-17 | Day 7 — Patient Data Capture | Collect patient name | Done | 100% | Fully implemented
2026-03-17 | Day 7 — Patient Data Capture | Collect patient phone number | Done | 100%
2026-03-17 | Day 7 — Patient Data Capture | Capture symptom description | Partial | 70%
2026-03-17 | Day 7 — Patient Data Capture | Attach notes to booking form | Pending | 0%
2026-03-17 | Day 7 — Patient Data Capture | Validate booking data transfer | Pending | 0%
2026-03-18 | Day 8 — Safety Guardrails | Add medical safety prompt | Partial | 60%
2026-03-18 | Day 8 — Safety Guardrails | Prevent diagnosis statements | Weak | 40% | Not enforced structurally
2026-03-18 | Day 8 — Safety Guardrails | Add fallback escalation message | Done | 80%
2026-03-18 | Day 8 — Safety Guardrails | Test safety edge cases | Pending | 0%
2026-03-18 | Day 8 — Safety Guardrails | Refine safe phrasing | Partial | 60%
2026-03-19 | Day 9 — System Testing | Test 50 simulated messages | Pending | 0%
2026-03-19 | Day 9 — System Testing | Test unsupported procedures | Pending | 0%
2026-03-19 | Day 9 — System Testing | Test booking link logic | Pending | 0%
2026-03-19 | Day 9 — System Testing | Test safety responses | Pending | 0%
2026-03-19 | Day 9 — System Testing | Fix discovered issues | Pending | 0%
2026-03-20 | Day 10 — Clinic Configuration | Create clinic_config_milena.json | Done | 90%
2026-03-20 | Day 10 — Clinic Configuration | Populate services and prices | Done | 85%
2026-03-20 | Day 10 — Clinic Configuration | Add booking link | Pending | 0%
2026-03-20 | Day 10 — Clinic Configuration | Run full conversation tests | Pending | 0%
2026-03-20 | Day 10 — Clinic Configuration | Prepare demo link | Pending | 0%